## Template information
Risk Termination Form
Field | Description
Risk ID | Unique risk identifier
Risk Description | Description of the risk
Root Cause | Cause of the risk
Inherent Risk Rating | High / Critical
Termination Justification | Why risk must be eliminated
Business Impact | Impact of termination
Approval Authority | Risk Committee / Board
Termination Actions | Steps taken
Completion Date | Date of termination
Residual Risk | None / Low
Closure Status | Closed

## Guidelines
Risk Termination (Risk Avoidance)
Risk termination means eliminating the activity that causes the risk, so the risk no longer exists.
Risk Termination – Procedure - Step-by-Step Process | Examples
Risk Identification & Assessment | Stopping a high-risk project
Risk ID | Discontinuing a non-compliant vendor
Inherent risk rating (High / Critical) | Removing a legacy system with severe security gaps
Business impact analysis | Exiting a high-risk market or geography
Feasibility Analysis
Cost of continuing vs terminating
Regulatory or contractual obligations
Business dependency analysis
Management Approval
Approval from Risk Committee / CRO / Business Head
Board approval for critical risks
Execution of Termination
Stop the activity/process/system/vendor
Decommission systems
Revoke access and contracts
Residual Risk Confirmation
Validate risk is eliminated
Ensure no secondary risks remain
Documentation & Closure
Update risk register
Archive evidence