## Project Plan
Risk Resolver Plan
| PROJECT TITLE |  | START DATE (MM/DD) |  | STATUS
| Risk Resolver |  | 2025-11-06 |  | Not Started
| PROJECT MANAGER |  | END DATE (MM/DD) |  | In Progress
| Shivendra Sharma Sir |  | 2026-01-15 |  | Complete
On Hold
S. NO. | TASK NAME | STATUS | PLANNED START DATE (MM/DD) | PLANNED END DATE (MM/DD) | ACTUAL START DATE (MM/DD) | ACTUAL END DATE (MM/DD) | DURATION in days | COMMENTS | References
1 | PROJECT CONCEPTION AND INITIATION
1.1 | – Project Charter Creation | Complete | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 1
1.2 | – Initial Research & Planning | Complete | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 1
1.2.1 | –– Stakeholder meetings | Complete | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 1
1.2.2 | ––Risk Resolver AI Workflow Design | Complete | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 1
1.2.3 | –– Project Initiation Approval | Complete | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 1
2 | TECHNICAL ENVIRONMENTAL SETUP
2.1 | – Python Environment Setup | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.2 | – Installing Required Libraries | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.2.1 | –– CrewAI Framework Installation | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.2.2 | –– Streamlit Installation | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.2.3 | –– Gemini AI API Setup | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.3 | – LLM Integration Planning | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.3.1 | –– Gemini API Configuration | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
2.3.2 | –– Model Selection | Complete | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 1
3 | PHASE 1: RAG KNOWLEDGE BASE DEVELOPMENT
3.1 | – Document Collection | Complete | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 1
3.2 | – RAG System Development | Complete | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 1
3.2.1 | –– Document Preprocessing | Complete | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 1
3.2.4 | –– Vector Store Creation | Complete | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 1
3.3 | – RAG Query System | Complete | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 1
3.3.1 | –– Similarity Search Implementation | Complete | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 1
3.3.2 | –– Context Retrieval Logic | Complete | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 1
3.3.3 | –– Gemini Integration for Answer Generation | Complete | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 1
3.4 | – RAG Testing & Validation | Complete | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 1
3.4.1 | –– Query Accuracy Testing | Complete | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 1
3.4.2 | –– Response Quality Evaluation | Complete | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 1
4 | PHASE 2: AGENTIC AI SYSTEM ARCHITECTURE
4.1 | – Agent Framework Design | Complete | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 1
4.1.1 | –– CrewAI Framework Selection | Complete | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 1
4.1.2 | –– Multi-Agent Orchestration Design | Complete | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 1
4.2 | – Agent Role Definition | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
4.2.1 | –– Agent 1: CIA Assessment Agent Design | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
4.2.2 | –– Agent 2: Risk Quantification Agent Design | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
4.2.3 | –– Agent 3: Control Discovery Agent Design | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
4.2.4 | –– Agent 4: Risk Decision Agent Design | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
4.2.5 | –– Agent 5: Excel Output Agent Design | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
4.3 | – RAG Tool Integration | Complete | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 1
5 | AGENT 1: CIA ASSESSMENT DEVELOPMENT
5.1 | – Agent Implementation | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.1.1 | –– Agent Configuration (Role, Goal, Backstory) | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.1.2 | –– RAG Tool Integration | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.1.3 | –– Task Definition | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.2 | – CIA Assessment Logic | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.2.1 | –– CIA Rating Determination Logic | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.3 | – Asset Valuation | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.3.1 | –– Asset Business Value Calculation | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
5.3.2 | –– Asset Criticality Classification | Complete | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 1
6 | AGENT 2: RISK QUANTIFICATION DEVELOPMENT
6.1 | – Agent Implementation | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.1.1 | –– Agent Configuration | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.1.2 | –– RAG Tool Integration | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.1.3 | –– Task Definition | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.2 | – Risk Impact Calculation | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.3 | – Risk Probability Calculation | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.4 | – Risk Value & Rating | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
6.4.1 | –– Risk Evaluation Rating Mapping | Complete | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 1
7 | AGENT 3: CONTROL DISCOVERY DEVELOPMENT
7.1 | – Agent Implementation | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
7.1.1 | –– Agent Configuration | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
7.1.2 | –– RAG Tool Integration | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
7.2 | – Control Discovery | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
7.3 | – Control Rating | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
7.4 | – Control Rating Calculation | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
7.5 | – Residual Risk Calculation | Complete | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 1
8 | AGENT 4: RISK MANAGEMENT AGENT
8.1 | – Agent Implementation | Complete | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 1
8.1.1 | –– Agent Configuration | Complete | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 1
8.1.2 | –– RAG Tool Integration | Complete | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 1
8.2 | – Risk management Decision Logic | Complete | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 1
8.3 | – Responsibility Assignment | Complete | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 1
9 | AGENT 5: EXCEL OUTPUT GENERATION
9.1 | – Excel Template Analysis | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
9.2 | – Excel Writer Development | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
9.2.1 | –– Asset Inventory Sheet Population | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
9.2.2 | –– Risk Assessment Sheet Population | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
9.2.3 | –– Risk Treatment Plan Sheet Population | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
9.3 | – Formula Preservation | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
9.4 | – Summary Report Generation | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10 | WEB UI DEVELOPMENT (STREAMLIT)
10.1 | – UI Design | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.1.1 | –– Main Page Layout | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.2 | – Backend Integration | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.2.1 | –– Agent Orchestration Logic | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.2.2 | –– Progress Tracking | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.3 | – Output Display | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.3.1 | –– Results Visualization | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.3.2 | –– Download Links Generation | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
10.4 | –– Summary Dashboard | Complete | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 1
11 | RISK COLLABORATION | [6 empty] | 28 th discussed on questionnare
11.1 | – Agent 0: Questionnaire Generator | Complete | 2025-12-08 | 2025-12-12 | 2025-12-08 | 2025-12-12 | 5 | Questionnaire systems for all treatment options + Follow-up tracking 28 th discussed om questionnare
11.1.1 | ––Agent 0 Core Logic Development | Complete | 2025-12-08 | 2025-12-09 | 2025-12-08 | 2025-12-09 | 2
11.1.2 | ––Dynamic Question Generation Logic | Complete | 2025-12-10 | 2025-12-11 | 2025-12-10 | 2025-12-11 | 2
11.1.3 | ––Questionnaire UI Integration | Complete | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 1
11.2 | – Treatment Plan Generator (Agent-4 Treatment plan) | Complete | 2025-12-22 | 2025-12-26 | 2025-12-22 | 2025-12-26 | 5
11.2.1 | ––Treatment Plan Template Discovery | Complete | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2025-12-23 | 2
11.2.2 | ––Implementation Details Generation | Complete | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2025-12-25 | 2
11.2.3 | ––Treatment Plan UI and Export | Complete | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 1
11.3 | – Acceptance Questionnaire & Form (Agent-4 acceptance questionnaire & form) | Complete | 2025-12-29 | 2026-01-02 | 2025-12-29 | 2026-01-02 | 5
11.3.1 | ––Acceptance Questionnaire Generator | Complete | 2025-12-29 | 2025-12-30 | 2025-12-29 | 2025-12-30 | 2
11.3.2 | ––Acceptance Form Generator | Complete | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 1
11.3.3 | ––Acceptance Workflow UI | Complete | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 1
11.4 | – Transfer Questionnaire & Form Generator (Agent-4 Transfer questionnaire & form) | In Progress | 2026-01-05 | 2026-01-07 |  |  | 3
11.4.1 | ––Transfer Questionnaire Generator | In Progress |  |  |  |  | 1
11.4.2 | ––Transfer Form Generator | In Progress |  |  |  |  | 1
11.4.3 | ––Transfer Workflow UI | In Progress |  |  |  |  | 1
11.5 | – Terminate Questionnaire & Form Generator (Agent-4 Terminate questionnaire & form) | In Progress | 2026-01-07 | 2026-01-09 |  |  | 3
11.5.1 | ––Terminate Questionnaire Generator | In Progress |  |  |  |  | 1
11.5.2 | ––Terminate Form Generator | In Progress |  |  |  |  | 1
11.5.3 | ––Terminate Workflow UI | In Progress |  |  |  |  | 1
11.6 | – Follow-Ups Tracking System | Complete |  |  |  |  | 1
11.6.1 | ––Follow-Up Page UI | Complete |  |  |  |  | 1
11.6.2 | ––Action Item Management | Complete |  |  |  |  | 1
11.6.3 | ––Acceptance, Treat, Terminate, Transfer Review Monitoring | Complete |  |  |  |  | 1
11.7 | – Risk Register System (Replaced Agent 5) | Complete | 2025-12-26 | 2026-01-08 | 2025-12-26 | 2026-01-08 | 14
11.7.1 | ––Risk Register Database Schema | In Progress | 2025-12-26 | 2025-12-30 | 2025-12-26 | 2025-12-30 | 5
11.7.2 | ––Risk Register Page UI | Complete | 2026-01-02 | 2026-01-08 | 2026-01-02 | 2026-01-08 | 7
11.8 | –Agent 0.5: Threat Discovery | In Progress |  |  |  |  | 1
11.8.1 | ––Threat Discovery Logic | In Progress |  |  |  |  | 1
11.8.2 | ––Threat Vocabulary Database | In Progress |  |  |  |  | 1
11.8.3 | ––Integration with Risk Assessment Pipeline | In Progress |  |  |  |  | 1
12 | PROJECT CLOSURE
12.1 | – Final Review | Not Started | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1
12.2 | – Lessons Learned Documentation | Not Started | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-15 | 1